Utility Monitor

Price List & Remaining Work — Planning Estimate

Draft for internal planning · September 2026

IMPORTANT — READ FIRST: Every number in this document is a planning-level estimate based on typical market rates and common hardware price ranges, NOT a vendor-verified quote. Actual hardware pricing must come from real vendor quotes once the client confirms their meter/sensor requirements (see the Scope of Work). Use this to plan and to have an informed conversation — not to commit a firm price to the client yet.

# Assumptions used in this estimate

- Currency: USD. Labor priced at a typical freelance/small-shop full-stack + IoT rate of $40–60/hour ($320–480/8-hr day) — adjust every figure below if your actual rate differs.

- Scale: 5–8 buildings in one portfolio (matching what has been built and demoed), a mix of Wi-Fi/vendor-API and Modbus-style connectivity assumed where the client hasn’t specified.

- Hardware prices are typical retail/distributor ranges for common IoT sensors and gateways as of this writing — real prices vary by brand, region, and order volume.

- Does not include your business’s margin/markup — add your own on top of the cost figures before quoting a client.

# What is already delivered (Phase 0)

The full software platform — dashboard, API, database, auth, multi-portfolio support, leak detection, email alerts, remote device control UI, installable web app — is built and demoed. For context, a comparable custom build from scratch typically runs $8,000–$18,000 at the labor rate above (roughly 20–40 developer-days). That cost has already been absorbed getting to this point — nothing further is owed for Phase 0 itself.

# Remaining work — effort and cost by phase

| Phase | Effort | Labor cost (est.) | What it covers |
| --- | --- | --- | --- |
| 1. Discovery | 2–4 days | $640 – $1,920 | Calls, site info gathering, confirming hardware/connectivity/thresholds/access needs |
| 2. Hardware & gateway setup | 3–7 days labor | $960 – $3,360 labor (+ hardware, see below) | Procuring, configuring, and installing the physical gateway(s) |
| 3. Live data integration | 5–10 days | $1,600 – $4,800 | Connecting real gateway output to the existing, already-tested ingestion API |
| 4. Production hardening | 10–20 days | $3,200 – $9,600 | Durable hosting/sessions, finer user roles, SMS/push alerts alongside email |
| 5. Rollout & handover | 3–5 days | $960 – $2,400 | Real-data threshold tuning, training, documentation, support handoff |
| Subtotal (labor only) | 23–46 days | $7,360 – $22,080 | Phases 1–5, excluding hardware and a native app |

# Hardware cost estimate (per building, typical ranges)

| Connectivity type | Typical hardware cost | Notes |
| --- | --- | --- |
| Vendor cloud API (meter already smart/connected) | $0 – $50/building | Little to no new hardware; mainly integration labor (Phase 3) |
| Wi-Fi retrofit sensor (tank ultrasonic level, energy pulse meter) | $40 – $120/building | Sensor unit only; needs existing Wi-Fi coverage at the site |
| Modbus/BACnet (needs a local gateway) | $80 – $200/building | Raspberry Pi or similar gateway (~$60–100) + protocol bridge software (free/open-source) |
| LoRaWAN | $60 – $150/building + $150–$400/gateway (shared across nearby buildings) | One gateway can often cover multiple nearby buildings, reducing per-building cost |
| Remote-controllable relay (per pump/valve) | $20 – $60/device | One per controllable device, e.g. the tank inlet pump already in the demo |

For 5–8 buildings, hardware typically lands in the $400–$1,600 range at these unit prices — confirm with real vendor quotes once connectivity is known.

# Ongoing costs (monthly, after launch)

| Item | Typical cost | Notes |
| --- | --- | --- |
| Hosting (small VPS/PaaS) | $5 – $25/month | This scale doesn’t need more than a small single instance |
| Email alerts | $0 – $10/month | Low volume; many providers’ free tiers cover this comfortably |
| SMS alerts (optional, e.g. Twilio) | ~$0.008 – $0.02/message | Only if SMS is added alongside email in Phase 4 |
| Domain name (optional) | $10 – $20/year | For a branded URL instead of a hosting provider’s default one |

# If a native mobile app is required

Not included above — the installable web app (PWA) already built covers "install to home screen, launch like an app" for most use cases at no extra cost. A true native app (separate iOS + Android builds, app store listings) is a substantially larger scope:

- Development: roughly 15–30 additional days ($4,800 – $14,400 at the same labor rate), depending on how much of the web dashboard’s functionality is reused vs. rebuilt natively.

- Apple Developer Program: $99/year. Google Play Developer: $25 one-time.

- Recommend confirming with the client whether this is a hard requirement before scoping it in.

# What is required to proceed (checklist)

- From the client: meter/sensor make & connectivity per building, network access confirmation, real thresholds, access/role requirements.

- Hosting account (e.g. a PaaS or small VPS provider) for durable deployment.

- An SMTP provider (or existing email account) for real alert delivery.

- If SMS is wanted: a Twilio (or similar) account.

- If a native app is wanted: Apple Developer and Google Play developer accounts.

- Physical access to each building to install sensors/gateways once hardware is chosen.

Utility Monitor — Price List & Remaining Work (Planning Estimate, not a vendor quote)